## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G11E069 |  | Project Name: |  | Coors Pavilion
NPDES Id. No. | NMR10052A & 52U |  | Location: |  | St Josephs St. NW
2022-11-08 |  | Owner |  |  |  | Contractor NMR10052U
Operator |  | Red Shamrock 4, LLC |  |  |  | Scarsguard Construction, LLC.
Contact name & title |  | Josh Skarsguard |  |  |  | Trish Kvern
e-mail |  | Josh@scarsguardfirm.com |  |  |  | trish@retailsouthwest.com
Contact Phone # |  | 262-2323 |  |  |  | 998-9093
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 11:00 -12:00 AM |  |  |  | Rain
Construction Phase: |  | Staging | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-10-16 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Silt Fence missing on Lots 5 and 8-B and though both have some gravel on them there still remains large bare spots so Final Stabilization Criteria isn't satisfied. Silt Fence Corrective Action required within 7 days. | [9 empty] | 2021-05-03
2 | The SWPPP map doen't reflect current site conditions because the SF is missing but not noted on the map and not addressed in a corrective action report. The Corrective action log and reports were missing from the SWPPP. | [9 empty] | 2021-05-31
3 | Sediment was in the street south and east of Lot 8-B and must be removed imideately. | [9 empty] | 2021-06-28
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | 2022-10-28
Notes:
There has been a lot of progress since the last inspection on 9/20/22; most of lot 8B is covered in gravel paving, lot 9C has a light coat of Hydroseed & Mulch, both lots 8C and 9C have SF next to paved areas, the NOI and ESC Plan have been approved by the City, and permit coverage is posted though it is still not ledgable from the street. The SWPPP was available and had current inspection reports, but no Corrective action log or current map.
Both the owner and contractor are operators and both signed the certification statement in the SWPPP and Delegated Authority to Trish Kvern Trish@retailsouthwest.com, 505-262-2323, who has the SWPPP at 8220 San Pedro DR. NE STE 500.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action