## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G12E002 |  | Project Name: |  | Caminito Verde Subdivision
NPDES Id. No. | NMR10077K |  | Location: |  | 2827 Rio Grande Blvd NW
2025-12-30 |  | Owner |  |  |  | Contractor
Operator |  | HG Development |  |  |  | Architectual Contractors, Inc
Contact name & title |  | Hunter Greene |  |  |  | Scooter Haynes
e-mail |  | hunter.greene@svn.com |  |  |  | scooter@scmpartners.com
Contact Phone # |  | 505-450-5612 |  |  |  | 505-898-6622
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-11-20 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | Posting - The permit coverage posting was missing from the site in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5.
2 | SWPPP - The SWPPP and self-inspection reports were not available on-site for the inspection in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a copy of the current SWPPP and all inspection reports at the site or at an easily accessible location so they can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3.
3 | BMPs - The construction exit has become clogged with excessive sediment in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
4 | Sediment - There is sediment being tracked out of the construction site in violation of CGP Part 2.2.4. Required mitigation: You must minimize sediment track-out by using appropriate stabilization techniques at all points that exit onto paved roads per CGP Part 2.2.4. Where sediment has been tracked-out from your site onto paved roads, sidewalks, or other paved areas outside your site, remove the deposited sediment by the end of the business day. Remove the track-out by sweeping, shoveling, or vacuuming these surfaces. You are prohibited from hosing or sweeping tracked-out sediment into any constructed or natural site drainage feature, storm drain inlet, or receiving water.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
The contractor states that track-out onto Rio Grande Blvd is being removed daily. Ensure that the sediment is not being washed down to a storm drain inlet. Proper maintenance of the construction exit will help minimize track-out.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action