## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G12E024 |  | Project Name: |  | Cinnamon Morning Subdivision
NPDES Id. No. | NMR1003QQ |  | Location: |  | 2714 Rio Grande Blvd NE
2021-04-08 |  | Owner |  |  |  | Contractor
Operator |  | Vivi Investments
Contact name & title |  | Steve Chavez
e-mail |  | steve.chavez505@yahoo.com
Contact Phone # |  | 505-415-9533
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: | 12:40 PM/12:50 PM |  |  | Rain
Construction Phase: |  | Pre-construction | [7 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  | 311/Complaint |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  | 74 |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2021-02-22 |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [9 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | No NPDES permit coverage posted
2 | Trash/debris
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no |  |  |  |  | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date:
Notes: | No BMPs are in place yet. There is plenty of garbage and other items throughout the site.
A telephone/electrical cable is hanging off of the pole in the adjacent yard to the North. It appears
to have once been connected to the metal pole laying on site.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action