## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G12E024 |  | Project Name: |  | Cinnamon Morning Subdivision
NPDES Id. No. | NMR1003QP/NMR1003QQ |  | Location: |  | 2714 Rio Grande Blvd NE
2021-07-01 |  | Owner |  |  |  | Contractor
Operator |  | Vivi Investments |  |  |  | Roku Development, LLC
Contact name & title |  | Steve Chavez |  |  |  | Steve Chavez
e-mail |  | steve.chavez505@yahoo.com |  |  |  | steve.chavez505@yahoo.com
Contact Phone # |  | 505-415-9533 |  |  |  | 505-415-9534
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 9:20 AM-9:30 AM |  |  | Rain
Construction Phase: |  | Grading/Earthwork | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 74 |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2021-06-28 |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | No perimeter BMP along West boundary of site. Install perimeter BMP as shown on the ESC Plan.
2
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | None on file
Notes: | No activity on the site during this inspecton. A worker from Guzman Construction was on
site fixing a bobcat.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action