## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G12E035 |  | Project Name: |  | Puerta Del Bosque
NPDES Id. No. | NMR10013N |  | Location: |  | Puerta Del Bosque Ln and Campbell Rd. NW
2021-05-12 |  | Owner |  |  |  | Contractor
Operator |  | Sivage Community Development LLC
Contact name & title |  | Steve Hernandez
e-mail |  | steve@dmcnm.com
Contact Phone # |  | 505-228-1401
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 1:25 PM/1:35PM |  |  |  | Rain
Construction Phase: |  | infrastructure/home construction | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-05-03 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | No posting of permit coverage. CLL sign is up, but the permit notice is not there. | [9 empty] | 2021-05-03
2 | Hole in silt fence. Maintain silt fences to prevent soil from entering the street.
3 | Clean washout area. Remove and dispose of hardened concrete and other waste per CGP 2.2.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-08-08
Notes: | No activity in the subdivision. Streets are clean
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action