## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G14E071 |  | Project Name: |  | Del's Hideaway
NPDES Id. No. | NMR1003DW |  | Location: |  | 4326 4th St. NW | [5 empty] | T Mcnaney <tmcnaney@twilighthomesnm.com>
2023-11-15 |  | Owner/contractor |  |  |  | DA
Operator |  | Twilight Homes | [8 empty] | 814 Solutions
Contact name & title |  | Tim McNaney |  |  |  | Alex Grannan
e-mail |  | tmcnaney@twilighthomesnm.com |  |  |  | agrannan@mtventerprises.com>
Contact Phone # |  | 505-975-1154 |  |  |  | 505 974-1627
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 930AM |  |  |  | Rain
Construction Phase: |  | Vertical | [9 empty] | Clear/ Windy
Type of Inspection: |  |  |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 65 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2023-09-14 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | The SWPPP was outdated, the copy of the CGP was for 2017 and expired February 2022 in violation of CGP Part 7.2.11. Required mitigation: You must include a copy of the current CGP in the SWPPP per CGP Part 7.2.11.c. | [9 empty] | 2021-05-03
2 | Concrete was washed out in the street instead of the provided concrete washout container in violation of CGP Part 2.3.4. An attempt to remove concrete from the street and curb drainage was incomplete. Required mitigation: You must direct wash water into a leak-proof container or leak-proof and lined pit designed so no overflows can occur due to inadequate sizing and locate any washout or cleanout activites as far away as possible from receiving waters, constructed or natural site drainage features, and storm drain inlets per CGP Part 2.3.4. | [9 empty] | 2021-05-31
3 | Sediment from excessive track-out was found along the street, in violation of CGP Part 2.2.4. Required mitigation: You must minimize sediment track-out by implementing addition track-out controls to ensure that sediment removal occurs prior to vehicle exit and where sediment has been tracked-out from your site onto paved roads, sidewalks or other paved areas outside of your site, remove the deposited sediment by the end of the same business day in which the track-out occurs per CGP Part 2.2.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | yes | Latest report Date: |  | 2023-11-08
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action