## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G14E071 |  | Project Name: |  | Del's Hideaway
NPDES Id. No. | NMR10033W |  | Location: |  | 4326 4th St. NW | [5 empty] | T Mcnaney <tmcnaney@twilighthomesnm.com>
2022-08-02 |  | Owner/contractor |  |  |  | DA
Operator |  | Twilight Homes | [8 empty] | 814 Solutions
Contact name & title |  | Tim Mcnaney |  |  |  | Alex Grannan
e-mail |  | tmcnaney@twilighthomesnm.com |  |  |  | agrannan@mtventerprises.com>
Contact Phone # |  | 505-975-1154 |  |  |  | 505 974-1627
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 9-10AM |  |  |  | Rain
Construction Phase: |  | Vertical | [9 empty] | Clear/ Windy
Type of Inspection: |  |  |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 90 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-07-30 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | none | [9 empty] | 2021-05-03
2 | [10 empty] | 2021-05-31
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | n/a | Latest report Date: |  | 2022-07-13
Notes: | SWPPP is at 8-14 solutions office and is up-to-date. DA to Alex Grannan
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action