## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G14E097 |  | Project Name: |  | Calle Cuarta
NPDES Id. No. | NMR1005D6 |  | Location: |  | 3525 4th St NW
2023-12-04 |  | Owner |  |  |  | Contractor
Operator |  | Yes Housing, Inc. |  |  |  | Pavilion Construction
Contact name & title |  | Page Ollice |  |  |  | Jared McCarn
e-mail |  | pollice@yeshousing.org |  |  |  | jmccarn@pavilionconstruction.com
Contact Phone # |  | 505-923-9607 |  |  |  | 505-668-8854
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1145am |  |  |  | Rain
Construction Phase: |  | grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-11-20 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP - Inspection reports were not available in violation of CGP Part 4.7.3. Ira Griffin of Pavilion Construction also needs to sign a Delegation of Authority to the Project Manager/Superintendent in accordance with CGP Appendix G.11.2. Required mitigation: You must keep a copy of all inspection reports at the site or at an easily accessible location, so that it can be made available at the time of an on-site inspection per CGP Part 4.7.3. Your SWPPP (including changes to your SWPPP), corrective action log, site inspection reports must be signed by the operator or by a duly authorized representative of that person per CGP Appendix G.11.2.
2 | BMPs - The silt fence along the northern perimeter along Fitzgerald Rd. and the block wall gaps on the southern perimeter is not entrenched in violation of CGP Part 2.2.3. The Construction Exit onto Fitzgerald Rd. has no track-out controls that has led to sediment track-out in violation of CGP Part 2.2.4. The sediment basins/ponds shown on the ESC Plans are undersized for construction activities in violation of CGP Part 2.2.12. Required mitigation: Install sediment controls along any perimeter areas of the site that are downslope from any exposed soil or other disturbed areas per CGP Part 2.2.3, a temporary berm along the perimeter is suggested. Minimize track-out by a)restrict vehicle use to properly designated exit points, b) use appropriate stabilization techniques at all points that exit onto paved roads, c)implement additional track-out controls as necessary to ensure that sediment removal occurs prior to vehicle exit, d) where sediment has been tracked-out from your site onto paved roads, sidewalks, or other paved areas, removed the deposited sediment by the end of the same business day in which the track-out occurs. Options include, but not limited to, installing wattles or entrenching silt fence along the perimeter of Fitzgerald Rd. and along the gaps in block wall on the south side of the site. Either install track-out controls at CE onto Fitzgerald Rd, use as an entrance only and exit onto 7th St., or do not use at all. Design the basins to provide storage for either i) the calculated volume from a 2-year, 24-hour storm, or ii) 3,600 cubic feet per acre drained per CGP Part 2.2.12.c. Amend the SWPPP map to reflect any changes made to on-site stormwater controls.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | requested | Latest report Date: |  | N/A
Notes:
Previous NOV for initiating land disturbance w/o BMPs
Ensure that any corrective actions taken to improve the construction exit is noted in the corrective action log of the SWPPP.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action