## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G14E097 |  | Project Name: |  | Calle Cuarta
NPDES Id. No. | NMR1005D6 |  | Location: |  | 3525 4th St NW
2023-12-14 |  | Owner |  |  |  | Contractor
Operator |  | Yes Housing, Inc. |  |  |  | Pavilion Construction
Contact name & title |  | Page Ollice |  |  |  | Jared McCarn
e-mail |  | pollice@yeshousing.org |  |  |  | jmccarn@pavilionconstruction.com
Contact Phone # |  | 505-923-9607 |  |  |  | 505-668-8854
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1015am |  |  |  | Rain
Construction Phase: |  | grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Rain |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-12-14 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | BMPs - The silt fence along Fitzgerald Rd. is still not entrenched in violation of CGP Part 2.1.2. There are no perimeter stormwater controls along the neighboring property (504 Fitzgerald Rd.) in violation of CGP Part 2.2.3. Required Mitigation: You must install all stormwater controls in accordance with good engineering practices, including applicable design specifications per CGP 2.1.2. Silt fencing requires entrenching in order to be an effective stormwater control. Install sediment controls along any perimeter areas of the site that are downslope from any exposed soil or other disturbed areas per CGP Part 2.2.3. The elevated pads that have been installed mean the perimeter is downslope of the disturbed soil.
2 | SWPPP - The self-inspection reports were unavailable at the time of the inspection in violation of CGP Part 4.7.3 and City Ordinance § 14-5-2-11. The SWPPP Map needs to be updated to reflect the current conditions regarding the construction support activity (fenced area on the neighboring property) in violation of CGP Parts 7.2.4 and 7.4.1. Required Mitigation: At a minimum, a routine compliance self-inspection once every 14 days and after any precipitation event of ¼ inch or greater until the site construction has been completed and the site has been determined as stabilized by the City per City Ordinance § 14-5-2-11 and CGP Part 4.2. You must keep a copy of all inspection reports at the site or at an easily accessible location, so that it can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3. The Site Map must include locations of on-site and off-site construction support activity areas per CGP Part 7.2.4.vii. You must modify your SWPPP, including the site maps, within seven days you make changes to your construction plans, stormwater controls, or other activities at your site that are no longer accurately reflected in your SWPPP per CGP Part 7.4.1. Amend the site map to reflect the current boundaries of the construction site including the portion of the neighboring property.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | requested | Latest report Date: |  | N/A
Notes:
Previous NOV for initiating land disturbance w/o BMPs
Ensure that any corrective actions taken to improve the construction exit is noted in the corrective action log of the SWPPP.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action