## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G14E097 |  | Project Name: |  | Calle Cuarta Apts. & TH WO
NPDES Id. No. | NMR100631/NMR100632 |  | Location: |  | 3525 4th St NW
2024-08-02 |  | Owner |  |  |  | Contractor
Operator |  | Calle Cuarta LLLP, YES Calle Cuarta TH, LLC |  |  |  | Pavilion Construction
Contact name & title |  | Page Ollice |  |  |  | Jared McCarn
e-mail |  | pollice@yeshousing.org |  |  |  | jmccarn@pavilionconstruction.com
Contact Phone # |  | 505-923-9607 |  |  |  | 505-668-8854
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1030am |  |  |  | Rain
Construction Phase: |  | verticals for apartments | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 90 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-06-30 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP Map has not been amended to include the storage/staging area on the neighboring property in violation of CGP Part 7.4.1. The self-inspection reports are not current in violation of CGP Part 4.7.3. Required mitigation: You must modify your SWPPP, including the site map(s), within seven days whenever make changes to your construction plans, stormwater controls, or other activities at your site that are no longer accurately reflected in your SWPPP per CGP Part 7.4.1.a. You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
2 | There was sediment track-out coming from a non-stabilized construction exit in violation of CGP Part 2.2.4. Required mitigation: Where sediment has been tracked-out from your site onto paved roads, sidewalks, or other paved areas outside of your site, remove the deposited sediment by the end of the same business day in which track-out occurs or by the end of the next business day if track-out occurs on a non-business day. Remove the track-out by sweeping, shoveling, or vacuuming these surfaces. You are prohibited from hosing or sweeping tracked-out sediment into any constructed or natural site drainage feature, storm drain inlet, or receiving water per CGP Part 2.2.4.d.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-05-13
Notes:
Report is for both the apartment site and the townhouse site
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action