## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G14E097 |  | Project Name: |  | Calle Cuarta Apts. & TH WO
NPDES Id. No. | NMR100631/NMR100632 |  | Location: |  | 3525 4th St NW
2025-02-13 |  | Owner |  |  |  | Contractor
Operator |  | Calle Cuarta LLLP, YES Calle Cuarta TH, LLC |  |  |  | Pavilion Construction
Contact name & title |  | Page Ollice |  |  |  | Jared McCarn
e-mail |  | pollice@yeshousing.org |  |  |  | jmccarn@pavilionconstruction.com
Contact Phone # |  | 505-923-9607 |  |  |  | 505-668-8854
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1030am |  |  |  | Rain
Construction Phase: |  | verticals for apartments, utilities for townhomes | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | BMPs - The perimeter silt fence on the north side along Fitzgerald Rd has collapsed in several sections and needs maintenance in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-02-03
Notes:
NMR1005D6 has been terminated. Replace NMR1005D6 with NMR100631 on the CGP Posting.
Report is for both the apartment site and the townhouse site.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action