## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G14E097 |  | Project Name: |  | Calle Cuarta Apts. & TH WO
NPDES Id. No. | NMR100631/NMR100632 |  | Location: |  | 3525 4th St NW
2025-06-23 |  | Owner |  |  |  | Contractor
Operator |  | Calle Cuarta LLLP, YES Calle Cuarta TH, LLC |  |  |  | Pavilion Construction
Contact name & title |  | Page Ollice |  |  |  | Jared McCarn
e-mail |  | pollice@yeshousing.org |  |  |  | jmccarn@pavilionconstruction.com
Contact Phone # |  | 505-923-9607 |  |  |  | 505-668-8854
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1:30pm |  |  |  | Rain
Construction Phase: |  | Interiors for apartments, paved | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 90 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-06-07 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Posting - The permit coverage was not posted at the perimeter of the construction site in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP part 1.5.
2 | Washout - There is concrete washout on bare soil in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or a leak-proof and lined pit designed so that no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-06-09
Notes:
Report is for both the apartment site and the townhouse site.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action