## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G14E097 |  | Project Name: |  | Calle Cuarta Apts. & TH
NPDES Id. No. | NMR100631/NMR100632 |  | Location: |  | 3525 4th St NW
2026-02-10 |  | Owner |  |  |  | Contractor
Operator |  | Calle Cuarta LLLP, YES Calle Cuarta TH, LLC
Contact name & title |  | Michelle DenBleyker
e-mail |  | mdenbleyker@yeshousing.org
Contact Phone # |  | 432-530-7978
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | Apartments completed, townhomes not started | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2026-01-08 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Stabilization - The townhome portion of the construction site has been inactive for more than 14 days and has no temporary or permanent stabilization measures in place in violation of CGP Part 2.2.14. Required mitigation: Initiate the installation of stabilization measures immediately in any areas of exposed soil where construction activities have permanently ceased or will be temporarily inactive for 14 or more calendar days, and complete the installation of stabilization measures as soon as practicable, but no later than 14 calendar days per CGP Part 2.2.14.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | ??
Notes:
Pavilion Construction has demobilized. The remainder of the disturbed land will need to install stabilization measures while the townhome portion remains inactive and until a new developer commences construction.
The SWPPP will need to remain on-site, and self-inspections will need to continue while CGP coverage is still active.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action