## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G17E021 |  | Project Name: |  | Raising Canes #852
NPDES Id. No. | NMR1004EV |  | Location: |  | 4800 Montgomery
2022-08-12 |  | Owner |  |  |  | Contractor
Operator |  | Raising Cane's Restaraunts, LLC |  |  |  | Guzman
Contact name & title |  | Robert Montgomery
e-mail |  | shawnp@lowesmarket.com
Contact Phone # |  | 806-786-0255
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 11:50am |  |  |  | Rain
Construction Phase: |  | Staging | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2022-08-01 |  |  |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | NPDES Permit wasn't posted for safe public viewing. Post sign per CGP 1.5. | [9 empty] | 2021-05-03
2 | The SWPPP wasn't available on site. Keep up-to-date SWPPP available on site. CGP 7.1 | [9 empty] | 2021-05-31
3 | BMPs were missing. Construct BMPs per approved details in 7 days or less. CGP 5 | [9 empty] | 2021-06-28
4 | Building was demiloshed and waste covered half of the site. 13. Dispose of construction and domestic waste in acceptable containers daily and use lids or tarps to cover waste containers when not in use per CGP 2.3.3.e | [9 empty] | 2021-07-06
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | required | Latest report Date: |  | none
Notes: | The construction trailer was open but crew couldn’t find SI or SWPPP.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action