## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G19E004A |  | Project Name: |  | La Mirada Shopping Center | [6 empty] | Gary Christensen
NPDES Id. No. | NMR10044X |  | Location: |  | Wyoming and Montgomery | [5 empty] | Roy Solomon | 720-8475
2024-11-15 |  | Owner |  |  |  | Contractor
Operator |  | Waymont LLC.
Contact name & title |  | Jarrod Likar VP
e-mail |  | jarrodl@aswinc.com
Contact Phone # |  | 505-896-9037
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 8:30 |  |  |  |  | Rain
Construction Phase: |  | Stabilization/inactive | [10 empty] | Clear/ Windy
Type of Inspection: |  | regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 50 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-11-07 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | BMPs - Silt fence down on south boundary | [9 empty] | 2021-05-03
2 | Sediment - Minor track out next to Tracts 6 & 8 | [9 empty] | 2021-05-31
3 | SWPPP map - must show transfers of Tracts 5, 6, & 8 and additional NOIs required. The SWPPP wasn’t inspected, but Bernalillo County records indicate:
3a | Several residential lots were transferred to Twilight Homes, which has an NOI and separate SWPPP.
3b | the remaining undeveloped residential lots and Tract 2-A of the Wymont Subdivision are all owned by “Wymont LLC, " the name on your NOI.
3c | two remaining undeveloped commercial Tracts, 6 & 8, have been transferred to “Mira AL SOL, LLC,” without NOI.
3d | Tract 5, currently under construction, was transferred to “ERC Wymont LLC” without NOI.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | N/A | Latest report Date: |  | N/A
Notes:
SWPPP is with Twighlight's
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | James Hughes
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action