## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G19E004A |  | Project Name: |  | Wymont Place Subdivision
NPDES Id. No. | In process |  | Location: |  | 8201 La Mirada Pl NE
2025-12-15 |  | Owner |  |  |  | Contractor
Operator |  | Stillbrooke Homes, Inc. |  |  |  | Stillbrooke Homes, Inc.
Contact name & title |  | Chris Kelsey
e-mail |  | ckelsey@stillbrooke.com
Contact Phone # |  | 505-858-1800
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 10:45am |  |  |  | Rain
Construction Phase: |  | verticals and grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 50 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-12-04 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | Washout - There is concrete washout on bare soil in Lots 17 and 18 in violation of CGP Part 2.3.4. Required mitigation: Direct wash water to a leak-proof container or a leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | In process | Latest report Date: |  | N/A
Notes:
Stillbrooke Homes, Inc. is in the process of developing a SWPPP (working with AMREP/Wymont LLC and Twilight) and filing for their NOI to be submitted to SWQ.
Ensure the SWPPP, inspection reports, and permit coverage posting will be on-site.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action