## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | G19E004G |  | Project Name: |  | Tract 5 Wymont Subdivision - Freddy's
NPDES Id. No. | NMR1006R0 |  | Location: |  | 4315 Wyoming Blvd NE
2025-05-12 |  | Owner |  |  |  | Contractor
Operator |  | ERC Wymont, LLC |  |  |  | Tanglewood Construction
Contact name & title |  | Jerry Rogers |  |  |  | Todd Granath
e-mail |  | jerry@erchospitality.com |  |  |  | Toddg@tanglewoodconstructionnm.com
Contact Phone # |  | 620-242-6033 |  |  |  | 505-668-0495
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1:45pm |  |  |  | Rain
Construction Phase: |  | verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-05-04 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | The self-inspection reports were not available at the time of the inspection in violation of CGP Part 4.7.3. Required mitigation: You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | no | Latest report Date: |  | N/A
Notes:
SWPPP is in the temporary construction office.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action