## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H09D017 |  | Project Name: |  | Mirehaven
NPDES Id. No. | NMR1000C1 |  | Location: |  | Mirehaven and Tierra Pintada
2021-04-23 |  | Owner |  |  |  | Contractor
Operator |  | Pulte, LLC.
Contact name & title |  | Kevin Patton
e-mail |  | kevin.patton@pultegroup.com
Contact Phone # |  | 505-238-2857
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: | 9:05 AM/9:20 AM |  |  |  | Rain
Construction Phase: |  | Stabilization | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  | 58 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2021-02-22 |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | None
2
3
4
5
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date:
Notes: | All homes completed. Site is stabilized with vegetation and landscaping.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action