## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  | Del Webb at Mirehaven PH 2
Location: |  | Tierra Pintada and Mirehaven Arroyo
Site Contact Name & Agency |  | Troy Crutchfield |  |  |  | ESC File No. | H09E017F
|  | Pulte Homes |  |  |  | NPDES Id. No. | NMR12AR19
Inspection Date: |  | 2019-05-17 | Start/End Time: |  | 1:00/1:50
CoA Stormwater Inspector: |  |  | Curtis Cherne | [9 empty] | Rain
Construction Phase: |  | vertical | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint | X | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear/ Windy |  |  | Temperature: ~ |  |  | 70 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2019-05-10 | [5 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [7 empty] | No
4 | Self Inspection Reports |  |  |  |  | Latest report Date: |  | 2017-05-14
Notes:
All previous issues were addressed
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Curtis Cheren PE 505-924-3420
|  | ccherne@cabq.gov |  |  |  |  | 2019-05-17

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action