## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H09E017G |  | Project Name: |  | Dell Webb Unit 3 & 4
NPDES Id. No. | NMR100C1 |  | Location: |  | Tierra Pintada & Mirehaven
2021-03-30 |  | Owner |  |  |  | Contractor
Operator |  | Pulte Homes |  |  |  | Pulte Homes
Contact name & title |  | Kevin Patton |  |  |  | Matt Sena, Lead Field Mgr II
e-mail |  | Kevin.Patton@pulte.com |  |  |  | Matt.Sena@pulte.com
Contact Phone # |  | 505-238-2857 |  |  |  | 505-603-7159
COA Inspector |  | Thomas Evans |  |  |  | Start/End Time: |  | 16:30 |  |  |  | Rain
Construction Phase: |  | infrastructure | [9 empty] | Clear/ Windy
Type of Inspection: |  | Complaint |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 72 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2021-02-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Repair silt fence along South border.
2 | Remove built-up soil against silt fences.
3 | Replace washout containments and clean washout facility. Clean up washout at Southwest corner.
4 | Add inlet protection.
5 | Pick up and dispose of trash/debris.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2020-07-30
Notes: | Inspection conducted as a result of a complaint about fugitive dust and a concern of soil
accumulation along the curbs near storm drains. It was noted that there was no visible fugitive dust
coming from the site, and the crew was using hoses to minimize dust. Inspectors did have a
conversation with Matt Sena on site to discuss the deficiencies/corrective actions.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Thomas Evans (505-803-6215)
tevans@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action