## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H09E017G |  | Project Name: |  | Dell Webb Unit 3 & 4
NPDES Id. No. | NMR100C1 |  | Location: |  | Tierra Pintada & Mirehaven | [6 empty] | Matt Sena
2022-01-06 |  | Owner |  |  |  | Contractor | [5 empty] | Matt.Sena@pulte.com
Operator |  | Pulte Homes |  |  |  | Pulte Homes | [5 empty] | 505-603-7159
Contact name & title |  | Kevin Patton |  |  |  | Ralph Garcia
e-mail |  | Kevin.Patton@pultegroup.com |  |  |  | ralph.garcia@pulte.com
Contact Phone # |  | 505-238-2857 |  |  |  | 505-980-4033
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 9:15 |  |  |  |  | Rain
Construction Phase: |  | Vertical/infrastructure | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 43 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2022-01-01 |  |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Previous areas of concern have been mitigated.
2 | Inlet Protection was missing on the lowest pair of inlets. Not critical since there isn't any sediment in the street and cutback swales are functioning.
3 | SWPPP was available at the construction trailer and was mosly up-to-date, but reports need operator signatures, date on inspector's signature, and dates of corrections after completion.
4 | Construction/domestic waste on the ground. Place waste in approved waste containers.
5 | Some minor washout where one of the pools was full and portland cement powder spill in street needs sweapt up (not washed off).
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | n/a | Latest report Date: |  | 2021-12-16
Notes:
SWPPP is signed by Kevin Patin with Delegation of Authority to the Pulte SSWR. (SSWR???)
The latest report dated 12/16/21 noted corrective actions needed on 12/23/21 and the inspector's signature isn't dated.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action