## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H09E020 |  | Project Name: |  | McDonald's (30-0236)
NPDES Id. No. | NMR1005LV |  | Location: |  | 1901 Ladera Dr NW
7/21/23 - 7/26/23 |  | Owner |  |  |  | Contractor
Operator |  | McDonald's USA LLC |  |  |  | Barnsly Construction
Contact name & title |  | Shanta Rodriguez-Williams |  |  |  | Dan Barnsley
e-mail |  | Shanta.Rodriguez@us.mcd.com |  |  |  | dan@barnsleyconstruction.com
Contact Phone # |  | 909-310-5886 |  |  |  | 505-264-0251
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: | 10am |  |  |  | Rain
Construction Phase: |  | infrastructure nearly complete | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2023-05-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Washout residue on bare soil away from a washout container and also leaking from a washout container in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or a leak-proof and line pit designed so no overflows can occur due to inadequate sizing or precipitation.
2 | SWPPP and inspection reports were not available during time of inspection in violation of CGP Parts 7.3, 4.7.3, and 5.4.3 Required mitigation: You must keep a current copy of your SWPPP at the site or at an easily accessible location so that it can be made available at the time of an on-site inspection per CGP 7.3. Inspection Reports and Corrective Action Logs must also be available at the site or at an easily accessible location, so that they can be immediately available at the time of an on-site inspection. At a minimum a routine compliance self-inspection is required to review the project for compliance with the Construction General Permit once every 14 days and after any precipitation event of 1/4 inch or greater per CGP 4.2 and City ESC Ordinance § 14-5-2-11(C)(1) until final acceptance of site stabilization by the city. Reports of these inspections shall be kept by the person or entity authorized to direct the construction activities on the site
3 | NPDES Posting was missing. CGP Part 1.5 states the requirement to post a notice of your permit coverage. You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date:
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action