## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H09E020 |  | Project Name: |  | McDonald's (30-0236)
NPDES Id. No. | NMR1005LV |  | Location: |  | 1901 Ladera Dr NW
2023-08-15 |  | Owner |  |  |  | Contractor
Operator |  | McDonald's USA LLC |  |  |  | Barnsly Construction
Contact name & title |  | Shanta Rodriguez-Williams |  |  |  | Dan Barnsley
e-mail |  | Shanta.Rodriguez@us.mcd.com |  |  |  | dan@barnsleyconstruction.com
Contact Phone # |  | 909-310-5886 |  |  |  | 505-264-0251
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:30am |  |  |  | Rain
Construction Phase: |  | infrastructure nearly complete | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-08-09 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | There are multiple violations with the SWPPP. Each operator's signatory must sign and date the SWPPP in accordance with Appendix G, Part G.11 to certify the SWPPP as per CGP Part 7.2.10. The NOI for each operator must be included in the SWPPP along with a copy of the 2022 CGP as per CGP 7.2.11. The Stormwater Team list is incomplete (no one identified to install and maintain BMPs) and there is no verification of training required by CGP Parts 6.2 and 6.3 as per CGP Part 7.2.2. Inspection reports were not signed by NOI holders in violation of CGP Part 4.7.2. There were no stabilization measure detailed in violation of CGP Part 7.2.6.vii. No construction schedule or phasing was included in violation of CGP Part 7.2.3. Required mitigation: Certify SWPPP in accordance with CGP 7.2.10. Add NOIs and 2022 CGP per CGP Part 7.2.11. Identify who installs and maintains BMPs per CGP Parts 6.1 and 7.2.2. Add training certifications for Stormwater Team members per CGP Parts 6.2 and 6.3. Sign Inspection reports per CGP Part 4.7.2. Identify stabilization measures, temporary and permanent per CGP Part 4.2.6.f. Add schedule or phases of construction per CGP Part 7.2.3.f. Modify the SWPPP Map to represent current on-ground status per CGP Part 7.4.1.
2 | NPDES Posting was missing. CGP Part 1.5 states the requirement to post a notice of your permit coverage. You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site.
See attached Notice of Violation for more details on required mitigation.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2023-08-14
Notes: | SWPPP is now located in construction office.
Previous violations for SWPPP, Posting , and Washout.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action