## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H09E020 |  | Project Name: |  | McDonald's (30-0236)
NPDES Id. No. | NMR1005LV |  | Location: |  | 1901 Ladera Dr NW
2024-01-25 |  | Owner |  |  |  | Contractor
Operator |  | McDonald's USA LLC |  |  |  | Barnsly Construction
Contact name & title |  | Shanta Rodriguez-Williams |  |  |  | Dan Barnsley
e-mail |  | Shanta.Rodriguez@us.mcd.com |  |  |  | dan@barnsleyconstruction.com
Contact Phone # |  | 909-310-5886 |  |  |  | 505-264-0251
COA Inspector |  | James Hughes |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | Open for business - landscaping not finished | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-01-04 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP and self-inspection reports were unavailable on-site in violation of City Ordinance § 14-5-2-11(C)(1). The restaurant was open for business, and there were not any construction personnel onsite. Required mitigation: Per City Ordinance § 14-5-2-11(C)(1), self-inspections must continue until the site is “determined as stabilized by the city.” The property owner/operator is responsible for determining when the “Conditions for Terminating CGP Coverage” per CGP Part 8.2 are satisfied and then for filing their Notice of Termination (NOT) with the EPA. Each operator may terminate CGP coverage only if one or more of the conditions in Part 8.2.1, 8.2.2, or 8.2.3 have occurred. After filing the NOT with the EPA, the property owner is responsible for requesting a Determination of Stabilization from the City. Email a copy of the latest self-inspection report to show compliance with the CGP and City Ordinance.
2 | Posting The sign posting your NPDES Permit coverage was missing. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way per CGP 1.5.
3 | Stabilization - landscaping still needs to be finished, and there is still about 700 square feet of bare dirt. Required Mitigation: Construction isn't complete until the site is completely stabilized
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | missing | Latest report Date: |  | 9/28/2023???
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action