## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  |  | Stormcloud Unit 4, The Ridge
Location: |  |  | Tierra Pintada & mirehaven Arroyo
Site Contact Name & Agency |  |  | Troy & Dan - Pulte |  |  |  | ESC File No. | H09E022A
|  |  | troy.crutchfield2@pulte.com |  |  |  | NPDES Id. No. | NMT1000BY
Inspection Date: |  |  | 2019-10-23 | Start/End Time: |  | 0745/0815hrs
CoA Stormwater Inspector: |  |  |  | Timothy E. Sims | [9 empty] | Rain
Construction Phase: |  |  | home construction | [10 empty] | Clear/ Windy
Type of Inspection: |  | x | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  |  | Clear |  |  | Temperature: ~ |  |  | 44* |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [9 empty] | 2019-10-04 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [13 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Washouts on the west side of White Squall. These washouts appear to be not related to Pulte's
construction activities. However, mitigate these washouts.
2 | 2001 White Squall requires a cut back behind drivepad cut out.
3 | 8808 Wind Sock waste not in acceptable container.
Yes
2.1 | Discharge off site? (Y/N) |  |  |  | No | [7 empty] | No
4 | Self Inspection Reports | [5 empty] | Latest report Date: |  | 2019-10-04
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  |  | Timothy E. Sims - (505) 803-6155
|  |  | tsims@cabq.gov |  |  |  |  | 2019-10-23

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action