## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H10E006A6 |  | Project Name: |  | 7501 La Morada Offices
NPDES Id. No. | NMR10070E |  | Location: |  | 7501 La Morada Pl NW
2025-06-03 |  | Owner |  |  |  | Contractor
Operator |  | 7501 La Morada LLC |  |  |  | All Seasons Roofing
Contact name & title |  | Ted Jaramillo |  |  |  | Ted Jaramillo
e-mail |  | ted@allseasonnm.com |  |  |  | ted@allseasonnm.com
Contact Phone # |  | 505-918-4111 |  |  |  | 505-918-4111
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 11:30 |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-06-02 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | BMPs - Some of the perimeter silt fencing has failed and needs maintenance in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective opertating condition during permit coverage per CGP Part 2.1.4.
2 | Sediment - The silt fence failure caused sediment to discharge into the City's storm drainage (curb and gutter to storm drain inlet) in violation of CGP Part 2.2.4. Required mitigation: Where sediment has been tracked-out onto paved roads, sidewalks or other paved areas outside of your site, remove the deposited sediment by the end of the same business day in which it occurs per CGP Part 2.2.4. Remove the sediment by sweeping, shoveling, or vacuuming these surfaces. You are prohibited from hosing or sweeping sediment into any drainage feature or storm drain inlet.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
The bare soil is causing both stormwater and air quality issues.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action