## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H10E006A7 |  | Project Name: |  | Vista Oriente Bldg 4
NPDES Id. No. | NMR1005EM |  | Location: |  | 2220 Unser Blvd NW
2024-12-26 |  | Owner |  |  |  | Contractor
Operator |  | Peterson INV-98th/Unser, LLC |  |  |  | Wilger Enterprises
Contact name & title |  | Douglas Peterson |  |  |  | Scot McLelland
e-mail |  | doug@petersonproperties.net |  |  |  | scot@wilger.com
Contact Phone # |  | 505-884-3578 |  |  |  | 505-345-2854
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 10:30am |  |  |  | Rain
Construction Phase: |  | foundation | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | The permit coverage posting was missing in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way.
2 | The certified SWPPP and signed self-inspection reports were unavailable because no one was on-site and there was no sign indicating the location of the SWPPP if the site was unmanned in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep an up-to-date copy of your SWPPP and all inspection reports at the site or at an easily accessible location, so that it can be made immediately available at the time of an on-site inspection per CGP Parts 4.7.3 and 7.3. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan's location must be posted near the main entrance of your construction site.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
One section of the construction fencing has fallen over.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action