## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H10E006A7 |  | Project Name: |  | Vista Oriente Bldg 4
NPDES Id. No. | NMR1005EM |  | Location: |  | 2220 Unser Blvd NW
2025-05-15 |  | Owner |  |  |  | Contractor
Operator |  | Peterson INV-98th/Unser, LLC |  |  |  | Wilger Enterprises
Contact name & title |  | Douglas Peterson |  |  |  | Scot McLelland
e-mail |  | doug@petersonproperties.net |  |  |  | scot@wilger.com
Contact Phone # |  | 505-884-3578 |  |  |  | 505-345-2854
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12:30pm |  |  |  | Rain
Construction Phase: |  | verticals | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-05-04 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | The on-site SWPPP has not been certified by both operators in violation of CGP Part 7.2.10. The self-inspection reports were unavailable during the inspection in violation of CGP Part 4.7.3 and City Ordinance §14-5-2-11. Required mitigation: Your signatory must sign and date your SWPPP in accordance with Appendix G, Part G.11. You must keep a copy of all inspection reports at the site or at an easily accessible location so they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | No | Latest report Date: |  | N/A
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action