## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H10E030 |  | Project Name: |  | Albuquerque RV & Boat Storage
NPDES Id. No. | NMR1005RN |  | Location: |  | 2201 Vista Oriente St. NW
2023-10-19 |  | Owner |  |  |  | Contractor
Operator |  | Ladera Enterprises
Contact name & title |  | Dan Rich, Principal |  |  |  | Leonard Bridge
e-mail |  | emeraldprops@aol.com |  |  |  | leonardbridge2@gmail.com
Contact Phone # |  | 505-304-4516 |  |  |  | 505-550-7033
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: | 11:30am |  |  |  | Rain
Construction Phase: |  | verticals, walls | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
[9 empty] | 75 |  | Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2023-09-14 |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP provided during the inspection was for the southern lot and no self-inspection reports were available in violation of CGP Part 4.7.3 and 7.3. Required mitigation: Provide the correct SWPPP and make available the self-inspection reports. Email the latest inspection report.
2 | The perimeter silt fence is in major disrepair and the disturbed land between the silt fence and block wall is not stabilized in violation of CGP Part 2.1.4 and 2.2.14. Required mitigation: Repair and maintain stormwater controls per CGP Part 2.1.4 and/or stabilize any areas of exposed soil where construction activities have permanently ceased or will be temporarily inactive for 14 or more calendar days per CGP Part 2.2.14.
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [5 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date:
Notes:
First City inspection since pandemic.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505-924-3325)
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action