## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H10E030 |  | Project Name: |  | Albuquerque RV & Boat Storage
NPDES Id. No. | NMR1005RN |  | Location: |  | 2201 Vista Oriente St. NW
2024-12-26 |  | Owner |  |  |  | Contractor
Operator |  | Ladera Enterprises
Contact name & title |  | Dan Rich, Principal |  |  |  | Leonard Bridge
e-mail |  | emeraldprops@aol.com |  |  |  | leonardbridge2@gmail.com
Contact Phone # |  | 505-304-4516 |  |  |  | 505-550-7033
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 10:45am |  |  |  | Rain
Construction Phase: |  | verticals, utilities | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 45 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-11-07 |  |  | 2021-02-22 | Sleet
Item Number | Deficiency/ Corrective Action
1 | None
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | 2024-07-22
Notes:
The posting's NPDES ID (NMR1000K2) is expired and is missing a phone number. Replace with the updated NPDES ID and a current phone number.
No one was on-site or in the office.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505-924-3325)
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action