## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H10E030 |  | Project Name: |  | Albuquerque RV & Boat Storage
NPDES Id. No. | NMR1000K2 |  | Location: |  | 2201 Vista Oriente St. NW
2021-08-30 |  | Owner |  |  |  | Contractor
Operator |  | Ladera Enterprises
Contact name & title |  | Dan Rich, Principal |  |  |  | Leonard Bridge
e-mail |  | emeraldprops@aol.com |  |  |  | leonardbridge2@gmail.com
Contact Phone # |  | 505-304-4516 |  |  |  | 505-550-7033
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | Excavation/grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 93 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2021-07-31 |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Washout in NE corner missed the liner and is laying on the ground. Pick up washout and dispose in proper waste container. Move Washout container to high ground.
2 | SWPPP was still not on site. The SWPPP must be up-to-date and available onsite at the next inspection.
3 | Silt Fence is not adequate for this large of a drainage area. Revise the BMPs to add properly sized diversion and sediment traps along the east boundary.
4
5
6
Yes
2.1 | Discharge off site? (Y/N) |  |  | Yes | [6 empty] | No
4 | Self Inspection Reports |  |  | provided | Latest report Date: |  | 2021-08-30
Notes: | Site is graded. Foundation and slabs are in progress. SF was reset on north side and
repaired around the rest of the site.
The reason that the violations had not been corrected is that the entire crew has Covid
and is in Quarantine. Please note that in the SWPPP!
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-803-6155)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action