## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
Project Name: |  | Vacant Lot Grading Vista Oriente
Location: |  | Unser & Vista Oriente |  |  |  | ESC File No. | H10E032A |  | NPDES Id. No. | not on file
Site Contact Name & Agency |  | Tuan Huynh |  |  |  | Phone: (o)
Phone: (m)
Owner |  | Tuan Huynh |  |  |  | Phone: (o) | 857-1444
Owner's e-mail |  | TuanvhNM@yahoo.com |  |  |  | Phone: (m) | 269-1418
Inspection Date: |  | 2020-07-29 | Start/End Time: |  | 0900/0930hrs
CoA Stormwater Inspector: |  |  | Timothy E. Sims | [9 empty] | Rain
Construction Phase: |  | earthwork | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint | x | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  |  | Temperature: ~ |  |  | 75* |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2020-07-25 | [5 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWQ acceptance and approval. Submit plans per program requirements from previous notification.
2 | Provide NPDES posting.
3 | Provide latest SWPPP self-inspection report.
4 | Install all BMP's per approved plan, (track-out pad).
perimeter sediment BMP in place and no signs of trackout. Site wheel rolled to minimize dust.
Progress has occurred with this site however additional modifications required
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [7 empty] | No
4 | Self Inspection Reports |  |  |  |  | Latest report Date: |  | not on file
Notes: | no conctact information for property owner forwarding to Stormwater Engineer.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Timothy E. Sims - (505) 803-6155
|  | tsims@cabq.gov |  |  |  |  | 2020-07-29

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action