## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H10E033 |  | Project Name: |  | 2200 Vista Oriente
NPDES Id. No. | NMR10036M |  | Location: |  | 2200 Vista Oriente
2023-10-19 |  | Owner |  |  |  | Contractor
Operator |  | Tuan Huynh
Contact name & title |  | Tuan Huynh
e-mail |  | tuanvhnm@yahoo.com
Contact Phone # |  | 505-269-1418
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1145am |  |  |  | Rain
Construction Phase: |  | none, weeds and partial land disturbance | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-09-14 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | There was no CGP coverage posting and land has been disturbed in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site per CGP Part 1.5.
2 | The SWPPP and self inspection reports were not available, nor was there a posting of the location if there is no personnel on-site in violation of CGP Parts 4.7.3 and 7.3. Required mitigation: You must keep a copy of the current SWPPP (7.3) and all inspection reports (4.7.3) at the site or at an easily accessible location so that it can be made available at the time of an on-site inspection. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan's location must be posted near the main entrance of your construction site. Please email the latest inspection report.
3 | The perimeter silt fence has decayed and virtually non-existent in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage per CGP Part 2.1.4.
4 | The site is still lacking compliant stabilization per CGP Part 2.2.14. The weeds are not sufficient vegetative cover and have become overgrown in violation of City Ordinance 9-8-4. The disturbed area needs stabilization. Required mitigation: Maintenance of weeds and stabilize the site if no construction activity for 14 or more calendar days as per CGP Part 2.2.14.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | N/A
Notes: | Recent land disturbance on east side of site.
Prior violations for Posting, SWPPP, BMPs, and stabilization
Weeds are becoming overgrown again and exceeding the 4" width and 4" height allowed by City Ordinance 9-8-4.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action