## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H10E033 |  | Project Name: |  | 2200 Vista Oriente
NPDES Id. No. | NMR10036M/NMR10060F |  | Location: |  | 2200 Vista Oriente
2024-01-12 |  | Owner |  |  |  | Contractor
Operator |  | Tuan Huynh
Contact name & title |  | Tuan Huynh
e-mail |  | tuanvhnm@yahoo.com
Contact Phone # |  | 505-269-1418
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | none, weeds and partial land disturbance | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 40 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-12-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The site is still lacking compliant stabilization per CGP Part 2.2.14. The weeds are not sufficient vegetative cover and have become overgrown in violation of City Ordinance 9-8-4. The disturbed area needs stabilization. Required mitigation: Maintenance of weeds and stabilize any recently disturbed soil at the site if no construction activity for 14 or more calendar days as per CGP Part 2.2.14.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2023-12-29
Notes: | Recent land disturbance on east side of site has been graded, but not stabilized
Prior violations for Posting, SWPPP, BMPs, and stabilization
Weeds are becoming overgrown again and exceeding the 4" width and 4" height allowed by City Ordinance 9-8-4.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action