## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H10E034 |  | Project Name: |  | Cactus Patch Plaza
NPDES Id. No. | NMR100433 |  | Location: |  | 7801 La Morado Pl NW
2023-10-17 |  | Owner |  |  |  | Contractor
Operator |  | Pacific Cactus, LLC | [9 empty] | mark.asplund@hakesbrothers.com
Contact name & title |  | Aaron Carlson
e-mail |  | aaron.carlson@yahoo.com
Contact Phone # |  | 506-6310
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 2:45pm |  |  |  |  | Rain
Construction Phase: |  | Landscaping | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 75 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-09-14 |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The NOI and permit coverage for this site expired February 17, 2022 and there was no submittal to continue permit coverage under the 2022 CGP, nor was there a Notice of Termination submitted. There is an estimated 1.1 acres of land disturbed without current CGP coverage in violation of CGP Part 1.4.3 and City Ordinance 14-5-2-11. Required mitigation: The operator of a site with 2017 CGP coverage were construction activities commenced prior to February 17, 2022 were required to submit a NOI no later than May 18, 2022 to continue permit coverage, as per CGP Part 1.4.3. The requirement for projects that disturb one acre or more must submit a current CGP NOI to the city is described in City Ordinance 14-5-2-11-(A).
2 | The permit coverage posting sign was on the ground and missing the NPDES ID and any contact information in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site per CGP Part 1.5.
3 | The SWPPP and self-inspection reports were unavailable and no information providing the location was posted, in violation of CGP Parts 4.7.3, 5.4.3, and 7.3. Required mitigation: You must keep a current copy of your SWPPP (7.3), all inspection reports (4.7.3), and corrective action log (5.4.3) at the site or at an easily accessible location so that it can be made available at the time of an on-site inspection. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site, according to CGP Part 7.3.
4 | The stockpiles were neither covered nor stabilized in violation of CGP Part 2.2.5.c. Required mitigation: You must manage your stockpiles composed of sediment and/or soil by providing cover or appropriate temporary stabilization for piles that will be unused for 14 or more days per CGP Part 2.2.5.c.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | N/a
Notes: | Provide latest self-inspection report.
Earthwork getting close to 500 cy, G&D Plan required if more than 500 CY
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505-924-3325)
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action