## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H10E034 |  | Project Name: |  | Cactus Patch Plaza
NPDES Id. No. | NMR1005ZF |  | Location: |  | 7801 La Morado Pl NW
2023-11-06 |  | Owner |  |  |  | Contractor
Operator |  | Pacific Cactus, LLC | [9 empty] | mark.asplund@hakesbrothers.com
Contact name & title |  | Aaron Carlson
e-mail |  | aaron.carlson@yahoo.com
Contact Phone # |  | 506-6310
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12pm |  |  |  |  | Rain
Construction Phase: |  | Stockpiles | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 75 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-09-14 |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The inspection reports were not signed by the operator in violation of CGP Part 4.7.2. Required mitigation: Each inspection report must be signed by the operator's signatory in accordance with Appendix G, Part G.11. A Delegation of Authority to a third party (Inspections Plus) is not accepted by the EPA, the delegated authority must be a representative of Pacific Cactus, LLC, persuant to CGP Appendix G, Part G.11.2. The reports may be signed electronically.
2 | The stockpiles were neither covered nor stabilized in violation of CGP Part 2.2.5.c. Required mitigation: You must manage your stockpiles composed of sediment and/or soil by providing cover or appropriate temporary stabilization for piles that will be unused for 14 or more days per CGP Part 2.2.5.c.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | yes | Latest report Date: |  | 2023-10-13
Notes:
Earthwork getting close to 500 cy, G&D Plan required if more than 500 CY. CGP coverage is now current and under review by EPA at the time of inspection.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505-924-3325)
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action