## 04.2019Form
|  | City of Albuquerque ---Stormwater Construction Site Inspection Report--- | [8 empty] | Weather: | Discharge: | Reports: | ROW:
General Information | [11 empty] | Shadow | Yes
ESC File # | H10E034 |  | Project Name: |  |  | Cactus Patch Plaza | [5 empty] | Yes | No
NPDES ID # | NMR1005ZF |  | Location: |  |  | 7801 La Morada Pl NW | [5 empty] | No | Requested | Sidewalk
2026-02-24 |  | Owner |  |  |  |  | Contractor |  |  |  | Snow |  | Out-of-date | Street
Operator |  | Pacific Cactus, LLC | [8 empty] | Clear |  | Unsigned | Storm Drain Inlet
Contact name & title |  | Aaron Carlson | [8 empty] | Rain |  |  | Drainage Ditch
Contact e-mail |  | aaron.carlson@yahoo.com | [8 empty] | Clear/Windy |  |  | Arroyo
Contact Phone # |  | 505-506-6310 | [8 empty] | Windy |  |  | Private Property
COA Inspector |  | Chancellor English |  |  |  |  | Start/End Time: |  | 1pm |  | Cloudy |  |  | N/A
Construction Phase: |  | Curbing, interiors | [8 empty] | Sleet
Type of Inspection: |  | Regular |  | Storm Event |  | Post Storm Event >0.25" |  |  | 311/Complaint | Follow Up
Weather at time of inspection: |  |  |  | Clear |  | Temperature: ~ |  | 60
Estimated date of last storm 0.25" or greater: |  |  |  |  | 2026-01-08
Item Number | Deficiency/ Corrective Action
1 | Washout - Concrete trucks are washing out onto bare soil in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or a leak-proof and lined pit designed so that no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
2 | BMPs - The construction exit is in poor condition and requires maintenance in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4.
Discharge off-site? |  | Shadow | Right-of-way: |  |  | Street |  | La Morada Pl NW
Self-Inspection Reports? |  | Yes | Latest report Date: |  |  | 2026-02-12
Notes:
The permit coverage posting is next to the construction exit. The SWPPP is in a doc-box mounted at the eastern corner of the property.
City of Albuquerque Stormwater Inspector Signature and date:
Contact information: Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action