## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H10E037 |  | Project Name: |  | ABA Baseball Fields
NPDES Id. No. | NMR1004L0 |  | Location: |  | 7500 La Morada Place NW
2023-10-18 |  | Owner |  |  |  | Contractor
Operator |  | Earlier Learning Solutions Foundation, Inc.
Contact name & title |  | David Bryant
e-mail |  | dbryant@lpelc.com
Contact Phone #
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1030am |  |  |  | Rain
Construction Phase: |  | Graded, inactive | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-09-14 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The SWPPP and self-inspection reports were unavailable at the time of inspection in violation of CGP Parts 4.7.3, 5.4.3, and 7.3. The contact on the permit coverage posting sign is no longer the contractor for the site and reported that the SWPPP was located in the office of the school. The contacts on the NOIs submitted to the City also no longer work at the school, and the staff could not locate the SWPPP. Required mitigation: You must keep a copy of the inspection reports (4.7.3), corrective action log (5.4.3), and SWPPP (7.3) at the site or at an easily accessible location so that it can be made immediately available at the time of an on-site inspection. CGP Part 7.3 also states that if an on-site location is unavoidable to keep the SWPPP when no personnel are present, notice of the plan's location must be posted near the main entrance of your construction site. City Ordinance 14-5-2-11 requires you to maintain the self-inspection schedule while the permit coverage is active.
2 | The construction seems to have ceased for more than 14 days with no stabilization measures installed in violation of CGP Part 2.2.14. Required mitigation: To minimize erosion, initiate the installation of stabilization measures immediately in any areas of exposed soil where construction activities have permanently ceased or will be temporarily inactive for 14 or more calendar days.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | N/A
Notes:
All contacts submitted to the City are no longer involved at the site.
Please provide the latest self-inspection report.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action