## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H10E0039 |  | Project Name: |  | 7501 La Morada LLC
NPDES Id. No. | NMR10070E |  | Location: |  | 7501 La Morada Pl NW
2025-11-18 |  | Owner |  |  |  | Contractor
Operator |  | 7501 La Morada LLC |  |  |  | All Seasons Roofing
Contact name & title |  | Ted Jaramillo |  |  |  | Ted Jaramillo
e-mail |  | ted@allseasonnm.com |  |  |  | ted@allseasonnm.com
Contact Phone # |  | 505-918-4111 |  |  |  | 505-918-4111
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 9:45am |  |  |  | Rain
Construction Phase: |  | Foundations | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 55 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-10-14 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | SWPPP - The inspection reports were not available at the time of the inspection in violation of CGP Part 4.7.3. Required mitigation: You must keep a copy of all inspection reports at the site or at an easily accessible location so that they can be made immediately available at the time of an on-site inspection per CGP Part 4.7.3.
2 | BMPs - Some of the perimeter silt fencing is damaged or not properly entrenched and needs maintenance in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective opertating condition during permit coverage per CGP Part 2.1.4.
3 | Washout - A significant amount of concrete washout around your washout pit, and the washout pit does not have a liner in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof container or leak-proof and line pit designed so no overflows can occur due to inadequate sizing or precipitation per CGP Part 2.3.4. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | N/A
Notes:
The SWPPP is mounted on the back of the posting sign. The key box code is 2404.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action