## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H11E075 |  | Project Name: |  | Playa del Sur
NPDES Id. No. | NMR1006DO |  | Location: |  | 5720 Miami Rd NW
2025-10-10 |  | Owner |  |  |  | Contractor
Operator |  | Butterfly Holdings, LLC
Contact name & title |  | Jarrod Likar
e-mail |  | jarrodl@aswinc.com
Contact Phone # |  | 505-596-9037
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1130am |  |  |  | Rain
Construction Phase: |  | Grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 75 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2025-09-14 |  |  |  | Sleet
Item Number | Deficiency/ Corrective Action
1 | Sediment is being tracked-out near storm drain inlets in violation of CGP Part 2.2.4. Required mitigation: Minimize sediment track-out by restricting vehicles to properly designated exit points, using appropriate stabilization techniques at all points that exit onto paved roads, and implementing additional track-out controls as necessary to ensure sediment removal per CGP Part 2.2.4. Where sediment has been tracked-out of your site onto paved roads, sidewalks, or other paved areas, remove the deposited sediment by the end of the same business day in which the track-out occurs. Remove the track-out by sweeping, shoveling, or vacuuming these surfaces. You are prohibited from hosing or sweeping tracked-out sediment into any constructed or natural site drainage feature, storm drain inlet, or receiving water.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2025-08-27
Notes:
Please send the most current self-inspection report.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action