## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H13E109A |  | Project Name: |  | Sandia Lab FCU
NPDES Id. No. | NMR1004MR & '4U0 |  | Location: |  | 1100 Rio Grande Blvd NW
2023-07-21 |  | Owner |  |  |  | Contractor
Operator |  | Garcia Real Estate Investments, LLC |  |  |  | Insight Construction
Contact name & title |  | Ed Garcia |  |  |  | Dave Brown
e-mail |  | eegarcia@garciacars.com |  |  |  | Dave@insightnm.com
Contact Phone # |  | 505-259-0339 |  |  |  | 505-506-8412
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 9am |  |  |  | Rain
Construction Phase: |  | Building and infrastructure | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 90 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2023-05-22 | [5 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Posting - Incomplete. Required mitigation: The NPDES ID # and contact names and phone numbers of both the owner and contractor are missing and must be included on the sign per CGP Section 1.5.
2 | SWPPP - certification page missing signatures of the owner and the contractor. Required mitigation: Your signatory must sign and date your SWPPP in accordance with Appendix G, Part G.11 as per CGP Section 7.2.10.
3 | Washout - Concrete debris and residue from washout is on the ground. Required mitigation: Remove and dispose contaminated soils and hardened concrete with other waste in per CGP 2.3.3.e. Direct all future wash water from concrete, paint, and stucco into a leak-proof container and do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground per CGP 2.3.4
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | yes | Latest report Date: |  | 2023-06-19
Notes:
Previous violations include Posting, Washout, and SWPPP inspection reports. SWPPP was located in connex.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505-924-3325)
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action