## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [10 empty] | NMR1003IY
ESC File No. | H13E113 |  | Project Name: |  | Avanyu Plaza
NPDES Id. No. | NMR10I07Y |  | Location: |  | 2500 12th Street NW | [5 empty] | Hart Construction; Andy Hart | Tim Kersh
2024-06-26 |  | Owner |  |  |  | Contractor |  |  |  |  | 505-345-4001 | 505-980-3609
Operator |  | IMPI6,LLC |  |  |  | Jaynes Corporation | [5 empty] | tkersh@hartconstruction.net
Contact name & title |  | Mark Thompson |  |  |  | Shad James
e-mail |  | mthompson@indianpueblo.com |  |  |  | shad.james@jaynescorp.com |  |  |  |  | Inspections Plus
Contact Phone # |  | 505-259-0362 |  |  |  | 505-345-8591
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 1:30pm |  |  |  |  | Rain
Construction Phase: |  | verticals | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 100 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2024-06-10 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | The permit coverage posting was missing in violation of CGP Part 1.5. Required mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The posting must be located so it is visible from the public road that is nearest to the active part of the construction site per CGP Part 1.5. | [9 empty] | 2021-05-03
2 | The perimeter silt fence needs maintenance in violation of CGP Part 2.1.4. Required mitigation: Ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage and are protected from activities that would reduce their effectiveness per CGP Part 2.1.4. | [9 empty] | 2021-05-31
3 | There was concrete washout on the ground in violation of CGP Part 2.3.4. Required mitigation: Direct wash water into a leak-proof and lined container or leak-proof and lined pit designed so no overflows can occur due to inadequate sizing or precipitation. Do not allow liquid wastes to be disposed of through infiltration or to otherwise be disposed of on the ground per CGP Part 2.3.4.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Yes | Latest report Date: |  | 2024-06-24
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action