## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [10 empty] | NMR1003IY
ESC File No. | H13E113 |  | Project Name: |  | Avanyu Plaza
NPDES Id. No. | NMR10I02Z |  | Location: |  | 2500 12th Street NW | [5 empty] | Hart Construction; Andy Hart | Tim Kersh
2023-05-08 |  | Owner |  |  |  | Contractor |  |  |  |  | 505-345-4001 | 505-980-3609
Operator |  | IMPI6,LLC |  |  |  | Hart Construction | [5 empty] | tkersh@hartconstruction.net
Contact name & title |  | Mark Thompson |  |  |  | Tim Kersh
e-mail |  | mthompson@indianpueblo.com |  |  |  | tkersh@hartconstruction.net |  |  |  |  | Inspections Plus
Contact Phone # |  | 505-259-0362 |  |  |  | 505-980-3609
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 9:20AM |  |  |  |  | Rain
Construction Phase: |  | Previous Building Permit shells complete - dirt pad sites along 12th St and Menaul | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 70 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2023-03-16 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | Permit coverage expired a year ago. You must renew your coverage under the Construction General Permit (CGP) and submit a copy of the NOI to the City for approval. | [9 empty] | 2021-05-03
2 | Permit coverage wasn't posted. You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of- way per CGP 1.5 | [9 empty] | 2021-05-31
3 | SWPPP wasn’t available on site at time of inspection, so it couldn't be checked to see if it is up-to-date. - Provide a scanned copy of the up-to-date SWPPP with all reports to the Storm Water Quality Section at 600 2nd St NW suite 400 - Jhughes@cabq.gov - Per CGP 4.8.2
4 | Silt Fence and Stabilization were missing from the dirt portion of this site. You must now apply cover per CGP 2.2.14 and install the missing silt fence.
5 | You must continue permit coverage, self-inspections, SWPPP and BMP maintenance until the City determines that the Final Stabilization Criteria CGP2.2.14.c has been satisfied Then you must remove the BMPs and send documentation of the Final Stabilization to the EPA with a Notice of Termination (NOT) per CGP 8.2 to end your coverage under the CGP.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | Requested | Latest report Date: |  | None on file
Notes: | Spoke with Mark Thompson who was unaware he still needed coverage.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action