## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H14E100A |  | Project Name: |  | Agenda Global Warehouse
NPDES Id. No. | NMR10045X |  | Location: |  | 1715 5TH St. NW
2022-03-30 |  | Owner |  |  |  | Contractor
Operator |  | Agenda Real Estate Holdings, LLC |  |  |  | T2 Building LLC
Contact name & title |  | Chris Taylor - Partner |  |  |  | Chris Taylor - Partner
e-mail |  | ctaylor@agenda-global.com |  |  |  | ctaylor@agenda-global.com
Contact Phone # |  | 505-450-4703 |  |  |  | 505-803-8582
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 9:30am |  |  |  | Rain
Construction Phase: |  | Excavation/grading | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Cloudy |  | Temperature: ~ |  |  | 53 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2022-03-23 |  |  | 2021-02-22 | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP not up-to-date. Operator signatures, NOIs, and CGP out of date. 2017 CGP must be updated to 2022. Self-inspection reports were missing.
2
3
Yes
2.1 | Discharge off site? (Y/N) |  |  | No | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | n/a
Notes:
Both the Agenda Real Estate Holdings, LLC and the T2 Building, LLC. NOIs (NMR10045X and NMR10045V respectively) are Certified by Chris Taylor aka Point of Contact . The 2017 NOIs were updated to 2022 but updated NOIs, 2022 CGP, and the 3/28/2022 Map were not in SWPPP that is available onsite. T2 deligation of authority is to Harold Stanley, HDStan, LLC. 505-803-8582 hstanley@hdstan.com a third party which isn't allowed.
Grading began on 3/29/22 after the Silt fence was placed around the perimiter, permit coverage was posted, there wasn't any sediment in the street, and the SWPOPP was available onsite but not up-to-date.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-924-3420)
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action