## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H14E100 |  | Project Name: |  | Agenda Global Warehouse
NPDES Id. No. | NMR10045X |  | Location: |  | 1715 5th St NW
2023-06-13 |  | Owner |  |  |  | Contractor
Operator |  | Agenda Real Estate Holdings, LLC |  |  |  | T2 Building LLC
Contact name & title |  | Chris Taylor - Partner |  |  |  | Harold Stanley
e-mail |  | ctaylor@agenda-global.com |  |  |  | hstanley@HDSTAN.com
Contact Phone # |  | 505-450-4703 |  |  |  | 803-8582
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: | 3pm |  |  |  | Rain
Construction Phase: |  | Construction | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  | 80 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2023-05-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | There were no BMPs installed at time of inspection. The ESC Plan shows a silt fence surrounding the perimeter. The CGP Section 2.1.4 states that you must ensure all stormwater controls are maintained and remain in effective operating condition during permit coverage.
2 | Washout was noted in several areas of the site, but no lined washout container. According to Section 2.3.4 of the CGP, you must direct wash water into a leak-proof container or leak-proof and lined pit; do not allow liquid wastes to be disposed of through infiltration or on the ground.
3 | The dumpster was not covered at the end of the work-day - contractors left during inspection. As per CGP Section 2.3.3.e, provide waste containers of sufficient size and number, and, for those without lids, provide a cover or similarly effective means designed to minimize the discharge of pollutants.
4 | SWPPP was unavailable during time of inspection and an effort to reach out to point of contact to locate the SWPPP failed. The SWPPP including Self Inspection Reports and Corrective Action Reports must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3 and 7.3. If an on-site location is unavailable to keep the SWPPP when no personnel are present, notice of the plan’s location must be posted near the main entrance of your construction site CGP 7.3. Self Inspections must also continue until NOT is filed and a determination of stabilization is determined by the city.
5 | During inspection, in an effort to locate the SWPPP, the phone number for a point of contact on the posting was incorrect. Section 1.5.b requires a contact name and phone number to call for construction site information. Update posting with correct contact information.
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | no | Latest report Date:
Notes: | 1 violation in 4/22 for out-of-date SWPPP
2 NOIs - different operator LLCs but same certifier
Of the 2 points of contact on the posting, 1 has an incorrect phone number, the other is a third
party, which is not allowed.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action