## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H14E100 |  | Project Name: |  | Agenda Global Warehouse
NPDES Id. No. | NMR10045X |  | Location: |  | 1715 5th St NW
2023-07-12 |  | Owner |  |  |  | Contractor
Operator |  | Agenda Real Estate Holdings, LLC |  |  |  | T2 Building LLC
Contact name & title |  | Chris Taylor - Partner |  |  |  | Harold Stanley
e-mail |  | ctaylor@agenda-global.com |  |  |  | hstanley@HDSTAN.com
Contact Phone # |  | 505-450-4703 |  |  |  | 803-8582
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: | 10am |  |  |  | Rain
Construction Phase: |  | Construction | [8 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [6 empty] | 2023-05-22 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [10 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | The NOI Posting is located in the construction parking area and not viewable from a safe, publicly available location in violation of CGP 1.5. The phone number listed for the owner, Agenda Real Estate Holdings, LLC, is incorrect and does not match the contact information on the NOI. Required Mitigation: You must post a sign or other notice of your permit coverage at a safe, publicly accessible location in close proximity to the construction site. The notice must be located so it is visible from the public road that is nearest to the active part of the construction site, and it must use a font large enough to be readily viewed from a public right-of-way per CGP 1.5. Ensure the NOI posting has a current owner point of contact name and phone numberfor obtaining additional construction site information per CGP 1.5.b.
2 | The up-to-date SWPPP and the Self-Inspection and Corrective Action Reports are not available on site in violation of CGP 7.1 and City Ordinance 14-5-2-11 Section C-1. Required Mitigation: The SWPPP, including Self Inspection Reports and Corrective Action Reports, must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3, and 7.3. City Ordinance 15-5-2-11 section C-1 states “Self-inspections by permittee. At a minimum a routine compliance self-inspection is required to review the project for compliance with the Construction General Permit once every 14 days and after any precipitation event of 1/4 inch or greater until the site construction has been completed and the site determined as stabilized by the city. Reports of these inspections shall be kept by the person or entity authorized to direct the construction activities on the site and shall be conducted during progress of the work, during work suspensions, and until final acceptance of site stabilization by the city. An owner's or his/her agent's failure to properly maintain records shall subject that owner to the penalty provisions of §§ 14-5-2-1 et seq.”
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [5 empty] | No
4 | Self Inspection Reports |  |  | no | Latest report Date:
Notes:
1 violation in 3/30/22 for out-of-date SWPPP, 1 prior violation (6/13/23) to missing SWPPP.
The NOI Owner point of contact phone number on the Permit Coverage Posting is incorrect and does not match the information on the NOI.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action