## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H14E100 |  | Project Name: |  | Agenda Global Warehouse
NPDES Id. No. | NMR10045X |  | Location: |  | 1715 5th St NW
2023-08-15 |  | Owner |  |  |  | Contractor
Operator |  | Agenda Real Estate Holdings, LLC |  |  |  | T2 Building LLC
Contact name & title |  | Chris Taylor - Partner |  |  |  | Harold Stanley
e-mail |  | ctaylor@agenda-global.com |  |  |  | hstanley@HDSTAN.com
Contact Phone # |  | 505-450-4703 |  |  |  | 803-8582
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12:30pm |  |  |  | Rain
Construction Phase: |  | Construction | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 95 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2023-08-09 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | None
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | yes | Latest report Date: |  | 2023-07-24
Notes:
1 violation in 3/30/22 for out-of-date SWPPP, 1 prior violation (6/13/23) to missing SWPPP.
All prior violations have been mitigated.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English (505) 924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action