## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information | [10 empty] | U-Haul Albuquerque Westside; 2217 4th Street NW
ESC File No. | H14E110 |  | Project Name: |  | U-Haul Albuquerque Westside | [5 empty] | NMR1003MS
NPDES Id. No. | NMR1003MS NMR1003MR |  | Location: |  | 2217 4th Street | [5 empty] | Amerco Real Estate Company; Tom Neill
2021-08-16 |  | Owner |  |  |  | Contractor |  |  |  |  | 505-259-0339
Operator |  | Amerco Real Estate Company |  |  |  | White Sands Construction |  |  |  |  | tom_neill@uhaul.com
Contact name & title |  | White Sands DA |  |  |  | David Malett
e-mail |  | tom_neill@uhaul.com |  |  |  | davidmalett@whitesandsconstruction.com
Contact Phone # |  | 505-259-0339 |  |  |  | 575-491-8208
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 1:15 PM-1:40 PM |  |  |  |  | Rain
Construction Phase: |  | Pre-construction, BMP's | [10 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Past Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  |  | Windy
Clear
Weather at time of inspection? |  |  |  | clear |  | Temperature: ~ |  |  | 93 |  |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [5 empty] | 2021-08-01 |  |  |  |  | 2021-02-22 |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [12 empty] | Fog
Item Number | Deficiency/ Corrective Action | [9 empty] | 2021-04-28
1 | All previous areas of concern have been mitigated. | [9 empty] | 2021-05-03
2 | [10 empty] | 2021-05-31
Yes
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | received | Latest report Date: |  | 2021-08-16 |  |  |  |  | Amerco Real Estate Company
Notes: | The Two Operators are 1) Curry McChristie mcchristie@whitesandsconstruction.com
President of White Sands Construction who's delegated authority is David Malett SI and Point
of Contact is Kimber Parsons kimber@whitesandsconstruction.com at 575-437-7816
2) Amerco Real Estate Company Tom Neill who's deligated authority is White Sands Construction
SWPPP is up-to-date, Site is Posted, CE is in - 8'overexcavation in progress.
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505-803-6215)
Jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action