## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H15E007 |  | Project Name: |  | Galles Chevrolet Parking Lot
NPDES Id. No. | NMR1005MK/NMR1006CY |  | Location: |  | 2001 and 2007 Candelaria Rd. NE
2024-08-19 |  | Lessee |  |  |  | Lessor
Operator |  | Galles Chevrolet Inc. |  |  |  | SAI Inc.
Contact name & title |  | Jamie Galles |  |  |  | Raul Modi
e-mail |  | jamiegalles@galles.com |  |  |  | saiinc1@yahoo.com
Contact Phone # |  | 505-506-9531 |  |  |  | 505-803-6544
COA Inspector |  | Chancellor English |  |  |  | Start/End Time: |  | 12:30pm |  |  |  | Rain
Construction Phase: |  | Bare dirt no construction activity at 2007 Candelaria | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 98 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [7 empty] | 2024-07-27 |  |  |  | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | SWPPP and self-inspection reports were unavailable on-site in violation of City Ordinance § 14-5-2-11(C)(1). Required mitigation: The SWPPP, including the SWPPP Map, Self Inspection Reports, and Corrective Action Reports, must be kept up-to-date per CGP 7.1 and available on-site per CGP 4.7.3, 5.4.3 and 7.3. Your SWPPP, corrective action log, site inspection, and any other compliance documentation required under this permit must be signed by the same responsible corporate officer who signs the certification statement on your NOI or by a duly authorized representative of that person per CGP Appendix G.11.2. Per City Ordinance § 14-5-2-11(C)(1), self-inspections must continue until the site is “determined as stabilized by the city.” The property owner/operator is responsible for determining when the “Conditions for Terminating CGP Coverage” per CGP Part 8.2 are satisfied and then for filing their Notice of Termination (NOT) with the EPA. Each operator may terminate CGP coverage only if one or more of the conditions in Part 8.2.1, 8.2.2, or 8.2.3 have occurred. After filing the NOT with the EPA, the property owner is responsible for requesting a Determination of Stabilization from the City. Email a copy of the latest self-inspection report to show compliance with the CGP and City Ordinance.
2 | BMPs - The silt fence (SF) was missing and/or not embedded around most of the site with sediment discharging downslope in violation of CGP 2.2.3. Required Mitigation: You must Install sediment controls along any perimeter areas of the site that are downslope from any exposed soil or other disturbed areas, as required by CGP 2.2.3. When the problem requires a new or replacement control or significant repair, install the new or modified control and make it operational or complete it by no later than seven (7) calendar days from discovery per CGP 5.2.1.
3 | Stabilization - The site is missing temporary or permanent stabilization in violation of CGP Part 2.2.14. Required mitigation: Initiate the installation of stabilization measures immediately in any areas of exposed soil where construction activities have permanently ceased or will be temporarily inactive for 14 or more calendar days and complete the installation of stabilization measures as soon as practicable, but no later than 14 calendar days per CGP Part 2.2.14.
2.1 | Discharge off site? (Y/N) |  |  | no | [6 empty] | No
4 | Self Inspection Reports |  |  | missing | Latest report Date: |  | ???
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Chancellor English 505-924-3325
cenglish@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action