## 04.2019Form
City of Albuquerque Stormwater Construction Site Inspection Report
General Information
ESC File No. | H15E068 |  | Project Name: |  | Maverik
NPDES Id. No. |  |  | Location: |  | 1901 Menaul blvd NE
2020-11-04 |  | Property Owner |  |  |  | Contractor
Operator |  | Maverik, Inc. |  |  |  | Maverik
Contact name & title |  | Troy Jergensen |  |  |  | Kelly Irons
e-mail |  | troy.jorgensen@maverik.com |  |  |  | Kelly.irons@maverik.com
Contact Phone # |  | 801-335-3851 |  |  |  | 801-419-2298
COA Inspector |  | Doug Hughes |  |  |  | Start/End Time: |  | 2pm |  |  |  | Rain
Construction Phase: |  | Earthwork | [9 empty] | Clear/ Windy
Type of Inspection: |  | Regular |  | Storm Event | Post Storm Event >0.25" |  |  | 311/Complaint |  | Follow Up |  | Windy
Clear
Weather at time of inspection? |  |  |  | Clear |  | Temperature: ~ |  |  | 76 |  |  | Cloudy
Estimated date of last storm 0.25" or greater | [11 empty] | Sleet
Clarify amount: ( i.e.. <1/4" to >3/4"): | [11 empty] | Fog
Item Number | Deficiency/ Corrective Action
1 | Silt fence not embeded and big gap (inpromptu entrance) at low point. Abandon the entrance in low corner and never have another hole in the silt fence again so long as this project lasts. Silt fence embedment is 12" minimum and faberik is 4' high per detail on approved plan.
2 | Construction debris not in acceptable container
3 | Inlet protection (sandbags around perimiter) three inlets in menaul in low corner.
4 | The ponds in the low corner are missing. See approved plan. It is supposed to be the first item of earthwork constructioon.
5 | Sediment in Menaul at inpromptu entrance and at c&g Construction must be removed daily.
6 | Where is the SWPPP?
7 | Provide SI contact info.
Yes
2.1 | Discharge off site? (Y/N) |  |  | Yes | [6 empty] | No
4 | Self Inspection Reports |  |  |  | Latest report Date: |  | 2020-11-06
Notes:
City of Albuquerque Stormwater Inspector Signature and date:
| Contact information: |  | Doug Hughes (505) 924-3420
jhughes@cabq.gov

## Addendum
ESC File No. |  | Addendum to Deficiency Items
Date
Item Number | Deficiency/ Corrective Action